## Introduction
Data Integration Project Planner
As a part of CIID Data Integration Toolkit, this project planner helps state teams identify, document and track the people and processes needed to integrate IDEA data into CEDS standards using Generate. Portions of this document can be modified after the initial project and adapted for ongoing SEA use to govern the people and processes beyond the intial project phase.
Who should use this resource?
Project Managers, EDFacts Coordinators, IDEA Part B Data Managers and technical staff should use this resource. Others such as leadership and other internal stakeholders may reference this document for context about the project or impacts to other related programs or projects within the organization.
What does the resource contain?
Each tab is a unique tool that can be used independently. The Roles and Responsibilities tab is designed to capture the initial, high-level roles and staff who will be requried to particpate in certain activities to support the project. Initial, high-level due dates are also captured here. The Communication Plan tab should document all the people and groups that need to recieve information about the data integration and Generate installation effort. The Calendar tab is used to visually track and identify related actvities that may impact staff availablity or resources needed during certain times. The Project Plan tab lists each step and task needed to complete the integration project of installing Generate and succesfully using it to submit EDFacts files.
How should the planner be used?
Follow the CIID Toolkit steps for prompts on when to use each tab of this planner during the intial data integration project. Each tab should be reviewed and updated with any new information if the project team members change, project scope changes or timing of activities is modified. Beyond the intial integration project, the tabs on this planner can be used annually to review, update and track activities needed to submit EDFacts files using Generate. SEA teams begin work on non-IDEA files, the tabs in this workbook can be modified for new projects.
This content was produced under U.S. Department of Education, Office of Special Education Programs, Award No. H373M200001. Amy Bae and Meredith Miceli serve as the project officers. The views expressed herein do not necessarily represent the positions or policies of the U.S. Department of Education. No official endorsement by the U.S. Department of Education of any product, commodity, service, or enterprise mentioned in this publication is intended or should be inferred.
https://ciidta.communities.ed.gov/#program

## Roles and Responsibilities
Roles and Responsibilities
Assigning roles and responsibilities is key to managing workloads and communicating project needs. Complete each row of the table below. Some areas of work may have several staff listed, for instance, multiple staff from various departments will be responsible for reviewing CEDS maps and data files.
More detailed tasks for the maintenance of data files by source system and report output can be tracked in the IDEA Part B Data Submission Organizer.
Project Management and Coordination | Role Responsible | Person Responsible | Back-up Person | Notes
Maintain project plan, coordinate work and timelines | ex: EDFacts Coordinator
Maintain communiation plan, ensure communication according to plan is occuring
Maintain project activities documentation; adjusting for changes in staff, activities or timing | ex: Project Manager or EDFacts Coordinator
CEDS
Create/maintain CEDS align maps and permissions (one per source system) | ex: Data Governance Coordinator
Create/maintain data dictionary metadata in each CEDS align map (by source system)
Review for new data elements or changes in data definitions in source data system | ex: IDEA Data Analyst, Directory data analyst
Facilitate CEDS Gap Analysis discussion and determinations | ex: Data Governance Coordinator
ETL
Write & maintain ETL code | ex: State ETL Developer
Document ETL checklist information
EDFacts and Reporting
Review and track EDFacts File Spec changes | ex: Part B Data Manager, EDFacts Coordinator
Perform data quality review of EDFacts files/reports created by Generate
Share additional Generate reports with stakeholders
Submission of EDFacts Files | ex: EDFacts Coordinator
Generate Release/Server
Contact person to receive notifications for new Generate releases and upgrade information
Install Generate updates/releases
Configure/maintain Generate server(s) and connections to source system(s) | ex: IT Server Administrator
Subject Matter Expert
Directory | ex: EDFacts Coordinator
Assessment
Personnel | ex: Part B Data Manager
Exiting
Discipline
Child Count

## Data Stewards and Sources
Data Stewards and Sources
Enter the name of the data steward and the local data source for each data collection. This information is important to maintain so that responsibility and location of data are clear to all members of the team.
Due Date | Data Source/EDFacts File Number | Content Area | Data Steward | Local Data Source (Database Name)
Last Friday in January | FS029— Directory/ Header file | General state and local educational agency data
First Wednesday in November | FS005 — Children with Disabilities (IDEA) Removal to Interim Alternative Educational Setting FS006 — Children with Disabilities (IDEA) Suspensions/Expulsions FS007— Children with Disabilities (IDEA) Reasons for Unilateral Removal FS088 — Children with Disabilities (IDEA) Disciplinary Removals FS143 — Children with Disabilities (IDEA) Total Disciplinary Removals FS144 — Educational Services During Expulsion | Discipline
First Wednesday in November | FS070 (DG486) — Special Education Teachers (FTE) FS099 (DG609) — Special Education Related Services Personnel FS112 (DG647) — Special Education Paraprofessionals | Personnel
First Wednesday in November | FS009 — Children with Disabilities (IDEA) Exiting Special Education | Exiting
Third Wednesday in December | FS175 — Academic Achievement in Mathematics FS178 — Academic Achievement in Reading (Language Arts) FS185 — Assessment Participation in Mathematics FS188 — Assessment Participation in Reading/Language Arts | Assessment
First Wednesday in April | FS002 — Children with Disabilities (IDEA) School Age FS089 — Children with Disabilities (IDEA) Early Childhood | Child Count

## Communication Plan
Communication Plan
A communication plan defines a project’s structure and the methods of information dissemination, establishing a process that: - ensures internal stakeholders are aware of progress; - creates an accountability structure for all involved parties; and - allows for mid-project corrections. Communication plans are important for determining and documenting the project stakeholders; identifying communication formats, vehicles, and schedules; establishing content of communications; and assigning parties responsible for particular communications. Complete the sections below to address the components of a communication plan.
Stakeholders
Document stakeholders, the types of information they require, and the vehicles to be used to provide or obtain information. Suggested stakeholder groups for project planning and progress updates include: SEA Leadership, representatives from other departments in the SEA (e.g., accountability, student information, federal programs), LEAs. Post-integration stakeholders might expand to schools and parents, to relate changes to data quality and public availability.
Stakeholder Name | Title | Contact Information | Type of Communication | Internal/External Communication
ex: Mary Smith | State Director of Special Education | (phone) 000-000-0000 (email) msmith@state.edu | Monthly Project Status Report | Internal
Project Meetings
Document all regularly scheduled project meetings and any other pertinent meetings related to the project.
Meeting Type | Purpose | Frequency | Meeting Leader | Participations/Location
ex: Status Update Meeting | Updates on project progress | Weekly | John Lyons, Director of Data | Adam Williams, Mary Smith, and Jane Phillips / Conference Room C
Project Documents
Maintain a running list of project documents for reference and/or dissemination.
Document Name | Description | Frequency | Document Owner | Comments or Distribution List
ex: Status Report | Communication of project progress | Weekly | John Lyons, Director of Data | Send document to all members of the data integration team
Other Communication Vehicles
Maintain a running list of other communication vehicles, aside from the project documents.
Communication Vehicle | Content/Purpose | Frequency | Communication Owner | Internal/External | Comments or Distribution List
ex: Newsletter | Update stakeholders on progress toward data integration | Monthly | John Lyons, Director of Data | Both Internal and External | Send newsletter to all identified stakeholders

## Project Plan
Project Plan
A project plan defines the project tasks and measures the progress towards completion of each step in a discreet project. The project plan: - ensures internal stakeholders are aware of progress; - creates an accountability structure for all involved parties; and - allows for mid-project corrections.
Code | Group Responsible | Section | Project and Task Name | Status | Progress | Start Date | End Date | Description | Deliverable | Milestone | Assignee (Lead) | Topics/Subtopics | Project Reference Notes | Other Project References | Comments
1 |  |  | Use Case
1.1 | ALL | Use Cases | Discuss and document Use Case(s) | Active
1.2 | ALL | Use Cases | Disseminate to leadership and stakeholders | Active
2 |  |  | Project plan (customize) and communication plan
2.1 | ALL | Project Plan | Create communication plan and modify project plan to state specifications | Inactive
| ALL | Project Plan | Document Roles and Responsibilities
3 |  |  | CEDS Alignment
3.1 |  |  | Diagram or Document State source systems in Enterprise Architecture document
3.2 | ALL | CEDS Alignment | Validate existing mapped elements
3.3 | ALL | CEDS Alignment | [State] sends CIID schemas for data collections in scope
3.4 |  |  | Special Education Alignment
3.4.1 | SPED | CEDS Alignment | Special Education data dictionary created/located for mapping
3.4.2 | SPED | CEDS Alignment | Special Education source tables aligned to CEDS
3.4.3 | SPED | CEDS Alignment | Verify Special Education source tables mapped to CEDS
3.5 |  |  | Assessment Alignment
3.5.1 | Assess | CEDS Alignment | Assessment data dictionary created/located for mapping
3.5.2 | Assess | CEDS Alignment | Assessment source tables mapped to CEDS
3.5.3 | Assess | CEDS Alignment | Verify Assessment source tables mapped to CEDS
3.6 |  |  | Child Count Alignment
3.6.1 | ChildCount | CEDS Alignment | Child Count data dictionary created/located for mapping
3.6.2 | ChildCount | CEDS Alignment | Child Count source tables mapped to CEDS
3.6.3 | ChildCount | CEDS Alignment | Verify Child Count source tables mapped to CEDS
3.6 |  |  | Discipline Alignment
3.6.1 | Discipline | CEDS Alignment | Discipline data dictionary created/located for mapping
3.6.2 | Discipline | CEDS Alignment | Discipline source tables mapped to CEDS
3.6.3 | Discipline | CEDS Alignment | Verify Discipline source tables mapped to CEDS
3.7 |  |  | Directory Alignment
3.7.1 | Directory | CEDS Alignment | Directory data dictionary created/located for mapping
3.7.2 | Directory | CEDS Alignment | Directory Information source tables mapped to CEDS
3.7.3 | Directory | CEDS Alignment | Verify Directory source tables mapped to CEDS
3.8 |  |  | Exiting IDEA Alignment
3.8.1 | Exiting | CEDS Alignment | Exiting data dictionary created/located for mapping
3.8.2 | Exiting | CEDS Alignment | Exiting source tables mapped to CEDS
3.8.3 | Exiting | CEDS Alignment | Verify Exiting source tables mapped to CEDS
3.8 |  |  | Personnel Alignment
3.8.1 | Personnel | CEDS Alignment | Personnel data dictionary created/located for mapping
3.8.2 | Personnel | CEDS Alignment | Personnel source tables mapped to CEDS
3.8.3 | Personnel | CEDS Alignment | Verify Personnel source tables mapped to CEDS
4 |  |  | Create Generate ETLs [Repeat this section for each migration]
4.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Grant the required access to the data for ETL developers
4.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Document business rules for ETL process in ETL checklist
4.3 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Create “test” data using previous year
4.3.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Recreate the current year EDFacts Child Count files (C002 and C089) using production data
4.3.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Recreate the current year EDFacts Personnel, Discipline, Exiting, and Assessments submission using production data
4.4 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Build ETLs from production environments
4.4.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETLs built to move Special Education (child count/EE for C002 and C089) (CDS) data to Generate
4.4.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETLs built to move Directory (CDS) data to Generate
4.4.3 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETLs built to move Special Education (discipline, exiting, personnel - NJ Smart) data to Generate
4.4.4 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETLs built to move Assessment data to Generate
4.4.5 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Review ETLs for Special Education (child count/EE for C002 and C089) with IT staff
4.4.6 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Review ETLs for Directory with IT staff
4.4.7 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Review ETLs for Special Education (discipline, exiting, personnel) with IT staff
4.4.8 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Review ETLs for Assessment with IT staff
4.5 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Execute the ETLs
4.5.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETL the C002 and C089 data into the Generate Application for the 2018 submission
4.5.1.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate successful load
4.5.1.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate data accuracy
4.5.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETL the Directory information into the Generate Application for the 2018 submission
4.5.2.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate successful load
4.5.2.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate data accuracy
4.5.3 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETL the Discipline, Exiting, and Personnel data into the Generate Application for the 2018 submission
4.5.3.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate successful load
4.5.3.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate data accuracy
4.5.4 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | ETL the Assessment data into the Generate Application for the 2018 submission
4.5.4.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate successful load
4.5.4.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Validate data accuracy
4.5.5 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Document process
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Source system data discovery
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Build Source to Staging ETL
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Run end to end data migration
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Test data for all data layers
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Rework ETL based on test results
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Match/legacy EDFacts files testing
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Run final submission data migration in Generate
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel | ETL | Create final submission file in Generate
5 |  |  | Generate application installation and configuration [universal step, can be done out of sequence]
5.1 |  |  | Set up development/test environment
5.1.1 | All | Installation | Web Server prepared in development environment for Generate Installation
5.1.2 | All | Installation | Generate installed in development environment
5.1.3 | All | Installation | Active Directory set up for account access in development
5.2 |  |  | Set up production environment
5.2.1 | All | Installation | Web server prepared in production environment for Generate installation
5.2.2 | All | Installation | Generate installed in production environment
5.2.3 | All | Installation | Active directory set up for account access in production
| All | Installation | Confirm SQL and Web server maintenance schedule with IT operations
| All | Installation | Confirm code management practice for state to ensure ETL code is maintained
6 |  |  | Generate File Review [repeat steps below for each data collection within scope]
6.1 |  |  | Year 1 File Matching
6.1.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Review the current year file submission in the Generate application for accuracy and compare to file submission counts done through normal process
6.1.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Run the IDC File Checker against the current year submission files (excluding directory)
6.2 |  |  | Year 2 (Production Year) File Testing and Submission
6.2.1 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Review [FS #] EDFacts files in the Generate application
6.2.2 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Run the IDC File Checker against the [FS #] submission files
6.2.3 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Submit [FS #] to EDFacts using Generate Report
6.2.4 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Review [FS #] reports in the Generate application
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Submit [FS #] to EDFacts using Generate Report
| SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Conduct After Action Review meeting
6.2.6 | SPED/Assess/ChildCount/Discipline/Directory/Exiting/Personnel |  | Document and plan for implementing changes based on After Action Review before beginning next data collection/future year file submission.
7 |  |  | Project Closing
7.1 |  |  | Complete IDEA Part B Data Submission Organizer and documentation, review as team
7.2 |  |  | CIID train state staff on procedures and maintenance
7.3
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Orange rows are slated for possible removal.

## Calendar
January | February | March | April
May | June | July | August
Sept | Oct | Nov | Dec

## Validation (hidden)
Progress
Not Started
In Progess
Complete